## Product Backlog
Group9: Dhairya Shah and Harsh Senjaliya
Ackermann Steering Controller for Autonomous Vehicle Module
Product Backlog | [5 empty] | Use index colors to show revisions on task time
Unique ID | Task | Sprint | Estimated time (minutes) | Time after Iteration 1 | Time after Iteration 2 | Index | Information
Target Time
1 | Plan and Design |  | 300 | 224 | 41 |  | Revised Target Time
1.1 | Set Up Project Directory | 1 | 10 | 8 | 0 |  | Actual Time Taken
1.2 | Create CMakeLists.txt for the Project | 1 | 15 | 12 | 3 |  | New Task Added
1.3 | Set up version control with Git | 1 | 10 | 10 | 0
1.4 | Install Google Test | 1 | 10 | 10 | 0
1.5 | Write initail README | 1 | 20 | 15 | 5
1.6 | Create UML diagrams | 1 | 15 | 10 | 5
1.7 | Prepare Phase 0 presentation | 1 | 15 | 10 | 5
1.8 | Genreate Phase 0 report | 1 | 10 | 8 | 2
1.9 | Setup Github Actions for CI | 1 | 10 | 10 | 0
1.1 | Setup CodeCov integration | 1 | 15 | 10 | 0
1.11 | Define Test strategy for the project | 1 | 15 | 12 | 0
1.12 | Plan refactoring sessions | 1 | 10 | 9 | 0
1.13 | Research Performance Optimizations for PID | 1 | 20 | 16 | 0
1.14 | Research Ackermann steering Control Algorithms | 1 | 20 | 13 | 0
1.15 | Plan for Test Coverage Improvement | 1 | 10 | 7 | 0
1.16 | Create PIDController Class | 1 | 15 | 8 | 7
1.17 | Write Test Cases for the PID controller Constructor | 1 | 15 | 8 | 7
1.18 | Create Ackermann Controller Class | 1 | 15 | 13 | 2
1.19 | Create Vehicle Class | 1 | 15 | 12 | 5
1.2 | Write Test Cases for the Ackermann Controller Constructor | 1 | 15 | 10 | 0
1.21 | Write Test Cases for Vehicle Class Constructor | 1 | 20 | 13 | 0
2 | Implementation |  | 480 | 0 | 0
2.1 | Implement basic PID logic | 2 | 15 | 0
2.2 | Write PID Controller SetParameters Method | 2 | 15 | 0
2.3 | Write Ackermann Steering method: ComputeSteering | 2 | 20 | 0
2.4 | Implement basic Ackermann Logic | 2 | 15 | 0
2.5 | Run initial tests for PID controller | 2 | 15 | 0
2.6 | Run initial tests for Ackermann Controller | 2 | 15 | 0
2.7 | Refactor Code for PID Controller | 2 | 15 | 0
2.8 | Refactor Code for Ackermann Controller | 2 | 20 | 0
2.9 | Improve Test Coverage for PIDController | 2 | 20 | 0
2.1 | Improve Test Coverage for Ackermann Controller | 2 | 20 | 0
2.11 | Prepare Demo For PIDController | 2 | 15 | 0
2.12 | Prepare Demo Ackermann Controller | 2 | 15 | 0
2.13 | Optimize Performance for PIDController | 3 | 20 | 0
2.14 | Optimize Performance for Ackermann Controller | 3 | 20 | 0
2.15 | Fix Bugs in PIDController | 3 | 15 | 0
2.16 | Fix Bugs in AckermannController | 3 | 15 | 0
2.17 | Make Sure PIDController is bug-free in Valgrind,cpp-lint and clang-tidy | 3 | 20 | 0
2.18 | Make Sure Ackermann Controller is bug-free in Valgrind,cpp-lint and clang-tidy | 3 | 20 | 0
2.19 | Run Final Tests for PIDController | 3 | 20 | 0
2.2 | Run Final Tests for Ackermann Controller | 3 | 20 | 0
2.21 | Perform Code Cleanup | 3 | 15 | 0
2.22 | Genrerate Performance Benchmarks | 3 | 20 | 0
2.23 | Update Doxygen Comments in PIDController | 3 | 15 | 0
2.24 | Update Doxygen Comments in Ackermann Controller | 3 | 15 | 0
2.25 | Run cpplint on final code | 3 | 10 | 0
2.26 | Run clang-tidy on final code | 3 | 10 | 0
2.27 | Run Valgrind in final code | 3 | 15 | 0
2.28 | Document lessons learned from PID implementation | 3 | 15 | 0
2.29 | Document lessons learned from Ackermann implementation | 3 | 15 | 0
| Remaining effort |  | 515
| Total effort time |  | 265

## Iteration backlog - 1
Group9: Dhairya Shah and Harsh Senjaliya
Ackermann Steering for Autonomous Vehicle Module
Iteration Backlog 1
Unique ID | Task | Target time (minutes) | Actual Time | Status
1 | Plan and Design | 390 | 184
1.1 | Setup Initial Cmake Project | 10 | 8 | Completed
1.2 | Setup Github Repository | 10 | 12 | Completed
1.3 | Install and Configure Gtest | 5 | 10 | Completed
1.4 | Setup Github CI Integration | 15 | 10 | Completed
1.5 | Create UML Diagram | 25 | 15 | Completed
1.6 | Write initial stub implementation for PIDController | 15 | 10 | Completed
1.7 | Write initial stub implementation for Ackermann Controller | 15 | 10 | Completed
1.8 | Implement PIDController constructor | 10 | 8 | Completed
1.9 | Implement Ackermann Controller constructor | 10 | 10 | Completed
1.1 | Write test cases fro PIDController Constructor | 20 | 10 | Completed
1.11 | Write test cases for Ackermann Controller Constructor | 20 | 12 | Completed
1.12 | Refine CMakeLists fro project structure | 15 | 9 | Completed
1.13 | Update README | 20 | 16 | In Progress
1.14 | Integrate CI pipeline with Unit Tests | 10 | 8 | Under Review
1.15 | Create initial documentation with Doxygen | 15 | 7 | In Progress
1.16 | Add coverage badges to github repository | 5 | 8 | Completed
1.17 | Perform initial debugging of PIDController | 20 | 8 | In Progress
1.18 | Perform initial debugging of Ackermann Controller | 20 | 13 | In Progress
1.19 | Code Review for PIDController | 15 |  | Not Started
1.2 | Code Review for Ackermann Controller | 15 |  | Not Started
1.21 | Run initial tests and validate results | 15 |  | Not Started
1.22 | Fix any anomalies in code | 20 |  | Not Started
1.23 | Run cpplint on current version of code | 15 |  | Not Started
1.24 | Run clang-tidy on current version of code | 15 |  | Not Started
1.25 | Run Valgrind on current version oif code | 15 |  | Not Started
1.26 | Fix and validate all errrors of cpplint, clang-tidy and Valgrind | 20 |  | Not Started

## Iteration backlog - 2
Group9: Dhairya Shah and Harsh Senjaliya
Ackermann Steering Controller for Autonomous Vehicle Module
Iteration Backlog 2
Unique ID | Task | Target time (minutes) | Actual Time | Status
2 | Implementation | 390 | 0
2.1 | Implement PIDController methods: SetParameters | 15 |  | Not Completed
2.2 | Implement Ackermann Controller methods: ComputeSteering | 15 |  | Not Completed
2.3 | Write unit tests for SetParameters in PIDController | 10 |  | Not Completed
2.4 | Write unit tests for ComputeSteering in Ackermann Controller | 10 |  | Not Completed
2.5 | Debug and Optimize SetParameters method | 5 |  | Not Completed
2.6 | Debug and Optimize Compute Steering method | 5 |  | Not Completed
2.7 | Refactor and clean up PIDController code | 5 |  | Not Completed
2.8 | Refactor and clean up Ackermann Controller code | 5 |  | Not Completed
2.9 | Write Doxygen comments for PIDController | 10 |  | Not Completed
2.1 | Write Doxygen comments for Ackermann Controller | 10 |  | Not Completed
2.11 | Run tests on PIDController methods | 15 |  | Not Completed
2.12 | Run tests on Ackermann Controller methods | 15 |  | Not Completed
2.13 | Update Unit tests for PIDController Methods | 5 |  | Not Completed
2.14 | Update Unit Tests for Ackermann Controller Methods | 5 |  | Not Completed
2.15 | Improve and Optimize PIDController | 10 |  | Not Completed
2.16 | Improve and Optimize Ackermann Controller | 10 |  | Not Completed
2.17 | Run final tests on PIDController | 20 |  | Not Completed
2.18 | Run final tests on Ackermann Controller | 20 |  | Not Completed
2.19 | Generate Performance Benchmark Reports | 10 |  | Not Completed
2.2 | Prepare Documentation using API usage examples | 15 |  | Not Completed
2.21 | Improve test coverage for both the controllers | 10 |  | Not Completed
2.22 | Refine UML Diagrams after Testing | 5 |  | Not Completed
2.23 | Final Debugging and Optimisation for PIDController | 20 |  | Not Completed
2.24 | Final Debugging and Optimisation for Ackermann Controller | 20 |  | Not Completed
2.25 | Run cpplint on final code | 15 |  | Not Completed
2.26 | Run clang-tidy on final code | 15 |  | Not Completed
2.27 | Run valgrind on final code | 15 |  | Not Completed
2.28 | Fix and validate issues from cpplint, clang-tidy or Valgrind | 20 |  | Not Completed
2.29 | Validate build and pass tests | 20 |  | Not Completed
2.3 | Update and make any changes to Doxygen comments. | 20 |  | Not Completed
2.31 | Document final results in README | 15 |  | Not Completed